## Home
project-state — Project Tracker v1.0
Consolidated source-of-truth workbook · Milestones · Deliverables · Risks · Gantt
Issued 2026-04-28 · Generated from .project-state/ substrate
Source sheets (edit these)
Milestones — 10 milestones with status, %, dates, deliverables, owner
Deliverables — 32 deliverables mapped to parent milestones
Risks — 11 open risks with likelihood, impact, score, mitigation
Phases — 4 agile-default lifecycle phases
Derived views (read-only)
Dashboard — live status summary computed from source sheets
Monthly Gantt — 12-month Gantt derived from milestone start/end weeks
Dependencies — milestone dependency map
Legend — color codes, status values, conventions

## Dashboard
project-state — Dashboard
Live status computed from source sheets. Do not edit directly.
OVERALL PROJECT STATUS
Project | project-state
Phase | 04-release
Pack | agile-default
Start date | 2026-04-24
Lead | David Olsson
Generated | 2026-04-28
MILESTONE SUMMARY
Total milestones | 10
Complete | 1
In progress | 0
Planned | 9
Total deliverables | 32
Deliverables complete | 4
RISK SUMMARY
Total open risks | 11
Critical (high/high) | 3
High impact | 4
Medium impact | 7

## Milestones
Milestones — source of truth (edit here)
ID | Owner | Title | Status | % Complete | Planned Start | Planned End | Actual Start | Actual End | Start Week | End Week | Technical Progress | Deliverable Count | Deliverables Complete
M01-v2-release | david-olsson-worksona | v2.0 Release — Generic Core + Compliance Packs | complete | 100 | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-04-27 | 1 | 1 | Released. 18 skills, 5 packs, full docs, migration script. | 4 | 4
M02-starter-pack-hardening | david-olsson-worksona | Harden Starter Packs to Production | planned | 0 | 2026-05-01 | 2026-06-30 |  |  | 2 | 10 |  | 4 | 0
M03-matrix-editor | david-olsson-worksona | Visual Reporting Matrix Editor | planned | 0 | 2026-06-01 | 2026-07-31 |  |  | 6 | 15 |  | 3 | 0
M04-pack-registry | david-olsson-worksona | Pack Registry — Install by Name | planned | 0 | 2026-07-01 | 2026-08-31 |  |  | 10 | 19 |  | 3 | 0
M05-compliance-packs-wave1 | david-olsson-worksona | Compliance Packs Wave 1 — Academic & Federal Research | planned | 0 | 2026-08-01 | 2026-10-31 |  |  | 15 | 28 |  | 3 | 0
M06-compliance-packs-wave2 | david-olsson-worksona | Compliance Packs Wave 2 — Industry & Regulatory | planned | 0 | 2026-10-01 | 2026-12-31 |  |  | 23 | 36 |  | 3 | 0
M07-multi-project-dashboard | david-olsson-worksona | Multi-Project Dashboard | planned | 0 | 2026-09-01 | 2026-11-30 |  |  | 19 | 32 |  | 3 | 0
M08-orchestrator-scheduling | david-olsson-worksona | Orchestrator Scheduling + Cron Integration | planned | 0 | 2026-06-15 | 2026-08-15 |  |  | 8 | 17 |  | 3 | 0
M09-substrate-validation-suite | david-olsson-worksona | Substrate Validation & Health Check Suite | planned | 0 | 2026-05-15 | 2026-06-30 |  |  | 4 | 10 |  | 3 | 0
M10-v21-release | david-olsson-worksona | v2.1 Release | planned | 0 | 2026-08-15 | 2026-09-15 |  |  | 17 | 21 |  | 3 | 0

## Deliverables
Deliverables — source of truth (edit here)
Deliverable ID | Milestone | Title | Status | Milestone Status | Milestone % Complete
D01a | M01-v2-release | Stakeholder reporting matrix | delivered | complete | 100
D01b | M01-v2-release | Pack system + 5 reference packs | delivered | complete | 100
D01c | M01-v2-release | Migration script (v1→v2) | delivered | complete | 100
D01d | M01-v2-release | Phase preset library (5 presets) | delivered | complete | 100
D02a | M02-starter-pack-hardening | client-services pack → production | planned | planned | 0
D02b | M02-starter-pack-hardening | board-investor pack → production | planned | planned | 0
D02c | M02-starter-pack-hardening | agile-default pack → production | planned | planned | 0
D02d | M02-starter-pack-hardening | open-source-community pack → production | planned | planned | 0
D03a | M03-matrix-editor | Matrix editor UI component (React) | planned | planned | 0
D03b | M03-matrix-editor | YAML round-trip serializer | planned | planned | 0
D03c | M03-matrix-editor | Validation in the editor (stakeholder refs, generator bindings) | planned | planned | 0
D04a | M04-pack-registry | Registry index format + hosting | planned | planned | 0
D04b | M04-pack-registry | Install/update CLI (pack install <id>) | planned | planned | 0
D04c | M04-pack-registry | Version constraint resolver | planned | planned | 0
D05a | M05-compliance-packs-wave1 | nserc-academic pack (Tri-Council reporting) | planned | planned | 0
D05b | M05-compliance-packs-wave1 | nih-rppr pack (NIH Research Performance Progress Report) | planned | planned | 0
D05c | M05-compliance-packs-wave1 | nsf-merit pack (NSF annual/final reports) | planned | planned | 0
D06a | M06-compliance-packs-wave2 | soc2-evidence pack (SOC2 audit evidence collection) | planned | planned | 0
D06b | M06-compliance-packs-wave2 | iso-27001 pack (ISO 27001 control attestation) | planned | planned | 0
D06c | M06-compliance-packs-wave2 | eu-horizon pack (EU Horizon periodic + final reports) | planned | planned | 0
D07a | M07-multi-project-dashboard | Multi-substrate reader (discover + scan N .project-state/ dirs) | planned | planned | 0
D07b | M07-multi-project-dashboard | Portfolio dashboard page (health, phase, deadlines) | planned | planned | 0
D07c | M07-multi-project-dashboard | Cross-project resource conflict detection | planned | planned | 0
D08a | M08-orchestrator-scheduling | Cron integration (launchd/systemd/cloud scheduler) | planned | planned | 0
D08b | M08-orchestrator-scheduling | Matrix tick engine (scan entries, compute due dates) | planned | planned | 0
D08c | M08-orchestrator-scheduling | Draft queue with notification on completion | planned | planned | 0
D09a | M09-substrate-validation-suite | Cross-reference integrity checker (stakeholder refs, milestone refs, person refs) | planned | planned | 0
D09b | M09-substrate-validation-suite | Schema drift detector (flag entities missing required fields) | planned | planned | 0
D09c | M09-substrate-validation-suite | Health score computation + dashboard widget | planned | planned | 0
D10a | M10-v21-release | v2.1 release bundle (skills + packs + docs + migration) | planned | planned | 0
D10b | M10-v21-release | Updated CHANGELOG, README, INSTALL | planned | planned | 0
D10c | M10-v21-release | Blog post: v2.1 announcement | planned | planned | 0

## Risks
Risks — source of truth (edit here)
ID | Title | Category | Likelihood | Impact | Score | Status | Owner | Mitigation | Contingency
R-01-single-maintainer | Single maintainer — bus factor of one |  | high | high | critical | open |  | Recruit at least one co-maintainer with write access. Prioritize PIC pack co-ownership (only production pack). Document the release process. Write a contributor onboarding guide. | Substrate files remain functional on disk as plain YAML. Another person can operate read-only. No new packs, features, or bug fixes ship until a new maintainer is found.
R-02-stale-orchestrator-refs | Orchestrator SKILL.md contains stale v1 skill references |  | high | medium | high | open |  | Update orchestrator SKILL.md to use generic v2 skill names (project-funder-reporting, project-review-meeting). Make routines conditional on whether the active pack provides those profiles. | Non-PIC users will see confusing orchestrator output referencing nonexistent skills. Workaround: document that quarterly/SC sections only apply when PIC pack is loaded.
R-03-no-tests-or-ci | Zero automated tests or CI/CD pipeline |  | high | high | critical | open |  | Add a minimal validation suite as first deliverable of M09: schema validators for manifest.yaml, reporting-matrix.yaml, milestone files, and pack profiles. Wire into a pre-commit hook or GitHub Action. Higher priority than M03 (matrix editor). | Without tests, validate manually before each release using a checklist. Create a scripts/validate-substrate.sh that checks required fields.
R-04-starter-packs-incomplete | Starter packs ship without declared profiles |  | high | medium | high | open |  | Either ship the missing profile YAMLs (e.g. agile-default.review-meeting, agile-default.phase-gate) or remove the provides.profiles entries from pack manifests. Do not declare capabilities the pack does not deliver. | Document clearly that starter packs require user-authored profiles before use. Add a startup validation check that warns when a loaded pack declares profiles that do not exist on disk.
R-05-scsiwyg-api-dependency | Hard dependency on scsiwyg API with no local fallback |  | medium | medium | medium | open |  | Add a local content cache that persists the last successful API response to disk. The regenerate script should snapshot blog content at build time so static exports don't depend on runtime API availability. | If scsiwyg goes down permanently, rewrite lib/scsiwyg.ts to read from local markdown files in a content/blog/ directory instead. Blog posts already exist as markdown in the API response body.
R-06-compliance-pack-depth | Compliance pack research depth — Wave 1 and Wave 2 are aspirational |  | high | medium | high | open |  | Descope to 1 pack per wave the maintainer has access to validate (e.g. NSERC). Solicit community contributions for others via blog and issue tracker. Reframe roadmap as community-driven rather than single-author. | If no domain experts contribute, publish packs as experimental maturity with clear warnings. Focus effort on making the pack authoring guide and PIC pack so exemplary that others can self-serve.
R-07-timeline-overload | Overlapping milestone timeline for a single person — 9 milestones in 5 months |  | high | high | critical | open |  | Ruthlessly prioritize. Highest-value milestones are M09 (validation suite — prevents silent corruption) and M02 (pack hardening — makes the system usable beyond PIC). Defer M03 (matrix editor), M07 (multi-project dashboard), and M04 (pack registry) to v2.2+. Accept that v2.1 will be smaller than planned. | If timeline slips, communicate openly via blog and changelog. Substrate format is stable — users are not blocked, they just don't get new features.
R-08-silent-error-swallowing | Silent error swallowing in website state and API layers |  | medium | medium | medium | open |  | Add structured error logging in state readers (console.error before returning fallback). Collect errors into a _diagnostics object for dev/admin mode. Add a validate command that checks all substrate files parse correctly. | Users can run js-yaml CLI directly against YAML files to find parse errors. Document as a troubleshooting step.
R-09-mcp-tool-stability | MCP tool stability and Claude Code coupling |  | medium | high | high | open |  | Document the MCP tools each skill depends on in a central manifest. Pin to specific MCP server versions where possible. Add a health-check routine that tests each MCP tool's availability before the orchestrator runs. | If MCP tools break, the substrate still works. Users lose surface automation (Slack posts, Gmail drafts, Calendar events) but can manually perform those actions. System degrades to 'generate artifacts on disk, deliver manually.'
R-10-no-community-infra | No contributor pipeline or community infrastructure |  | high | medium | high | open |  | Push to a public GitHub repository with LICENSE, CONTRIBUTING.md, issue templates, and discussion forum. Make the PIC pack a showcase. Write a 'Your First Pack' tutorial as a blog post. | Accept the system serves a niche of one (maintainer's own projects) and optimize for that use case rather than pursuing generality.
R-11-website-path-assumption | Website state loading uses fragile relative path assumption |  | medium | medium | medium | open |  | Add a build-time data snapshot step: serialize all substrate data into JSON files inside the website directory so the deployed site doesn't depend on filesystem access to ../. Use a prebuild script that copies substrate YAML into content/ before next build runs. | For Vercel deployment, the current approach works because Vercel uploads the entire directory including parent paths. If deployed from a monorepo or CI, the prebuild step becomes mandatory.

## Phases
Phases — source of truth (edit here)
Phase | Name | Description | Start Week | End Week
01-discovery
02-build-loops
03-hardening
04-release

## Monthly Gantt
Monthly Gantt — derived from Milestones
Collapsed view for sharing/printing. Cells are computed from milestone dates.
ID | Title | Status | Apr '26 | May '26 | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27
M01-v2-release | v2.0 Release — Generic Core + Compliance Packs | complete | C
M02-starter-pack-hardening | Harden Starter Packs to Production | planned |  | P | P
M03-matrix-editor | Visual Reporting Matrix Editor | planned |  |  | P | P
M04-pack-registry | Pack Registry — Install by Name | planned |  |  |  | P | P
M05-compliance-packs-wave1 | Compliance Packs Wave 1 — Academic & Federal Research | planned |  |  |  |  | P | P | P
M06-compliance-packs-wave2 | Compliance Packs Wave 2 — Industry & Regulatory | planned | [6 empty] | P | P | P
M07-multi-project-dashboard | Multi-Project Dashboard | planned | [5 empty] | P | P | P
M08-orchestrator-scheduling | Orchestrator Scheduling + Cron Integration | planned |  |  | P | P | P
M09-substrate-validation-suite | Substrate Validation & Health Check Suite | planned |  | P | P
M10-v21-release | v2.1 Release | planned |  |  |  |  | P | P

## Dependencies
Dependencies — milestone dependency map
Milestone | Status | % Complete | Depends on | Provides to
M01-v2-release | complete | 100 | — | M02, M09
M02-starter-pack-hardening | planned | 0 | M01 | M05, M06, M10
M03-matrix-editor | planned | 0 | M01 | M10
M04-pack-registry | planned | 0 | M01 | M05, M06, M10
M05-compliance-packs-wave1 | planned | 0 | M02, M04 | M10
M06-compliance-packs-wave2 | planned | 0 | M02, M04 | M10
M07-multi-project-dashboard | planned | 0 | M01 | M10
M08-orchestrator-scheduling | planned | 0 | M01 | M10
M09-substrate-validation-suite | planned | 0 | M01 | M10
M10-v21-release | planned | 0 | M02, M03, M04, M08, M09 | —

## Legend
Legend
Status values
planned | Not yet started
in_progress | Work underway
complete | Done
at_risk | Behind schedule or blocked
delivered | Deliverable accepted
Risk scores
critical | high × high
high | high × medium or medium × high
medium | any other combination with medium
low | low × low or low × medium