# project-state — Project Plan and Timeline

Date: 2026-04-28  ·  Phase: 04-release  ·  Pack: agile-default

## Project overview

Generic operational substrate for multi-stakeholder projects. Provides 18 project-* skills
and 5 compliance packs that turn any project into a system where routine reporting is a
byproduct of normal work.

## Lifecycle phases

project-state uses the agile-default phase preset with four phases. The project is currently in phase 04-release following the v2.0 launch.

| Phase ID | Name | Description |
| --- | --- | --- |
| 01-discovery |  |  |
| 02-build-loops |  |  |
| 03-hardening |  |  |
| 04-release |  |  |

## Milestone summary

The project has 10 milestones spanning from April 2026 through December 2026. M01 (v2.0 release) is complete. Nine milestones remain planned for v2.1 and beyond.

| ID | Title | Status | % Complete | Start | End |
| --- | --- | --- | --- | --- | --- |
| M01-v2-release | v2.0 Release — Generic Core + Compliance Packs | complete | 100% | 2026-04-24 | 2026-04-27 |
| M02-starter-pack-hardening | Harden Starter Packs to Production | planned | 0% | 2026-05-01 | 2026-06-30 |
| M03-matrix-editor | Visual Reporting Matrix Editor | planned | 0% | 2026-06-01 | 2026-07-31 |
| M04-pack-registry | Pack Registry — Install by Name | planned | 0% | 2026-07-01 | 2026-08-31 |
| M05-compliance-packs-wave1 | Compliance Packs Wave 1 — Academic & Federal Research | planned | 0% | 2026-08-01 | 2026-10-31 |
| M06-compliance-packs-wave2 | Compliance Packs Wave 2 — Industry & Regulatory | planned | 0% | 2026-10-01 | 2026-12-31 |
| M07-multi-project-dashboard | Multi-Project Dashboard | planned | 0% | 2026-09-01 | 2026-11-30 |
| M08-orchestrator-scheduling | Orchestrator Scheduling + Cron Integration | planned | 0% | 2026-06-15 | 2026-08-15 |
| M09-substrate-validation-suite | Substrate Validation & Health Check Suite | planned | 0% | 2026-05-15 | 2026-06-30 |
| M10-v21-release | v2.1 Release | planned | 0% | 2026-08-15 | 2026-09-15 |

## Timeline

Apr 2026: M01 v2.0 Release (COMPLETE)
May–Jun 2026: M02 Starter Pack Hardening, M09 Validation Suite
Jun–Aug 2026: M03 Matrix Editor, M08 Orchestrator Scheduling
Jul–Aug 2026: M04 Pack Registry
Aug–Sep 2026: M10 v2.1 Release
Aug–Oct 2026: M05 Compliance Packs Wave 1
Sep–Nov 2026: M07 Multi-Project Dashboard
Oct–Dec 2026: M06 Compliance Packs Wave 2

## Critical path

M01 → M02/M09 → M03/M04/M08 → M10 (v2.1 release)
M02/M04 → M05/M06 (compliance packs depend on hardened starters + registry)

## Surfaces and reporting

| Surface | Status | Usage |
| --- | --- | --- |
| Blog (scsiwyg) | Enabled | Weekly status, sprint retros |
| Website (Vercel) | Enabled | Reference docs, auto-deploy |
| Slack | Disabled | — |
| Gmail | Disabled | — |
| Calendar | Disabled | — |